## RACI Template
Milestone | Deliverable | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I)
Project Phase | Specific Output/Task | Does the work | Owns the decision | Provides input | Kept in the loop
Project Initiation | Project Charter | Project Manager | Sponsor | Team Leads | All Team Members
Project Initiation | Stakeholder Analysis | Business Analyst | Project Manager | Sponsor | Team Leads
Planning | Project Plan | Project Manager | Sponsor | Team Leads, SMEs | Stakeholders
Planning | Risk Assessment | Risk Manager | Project Manager | Team Leads | Sponsor
Execution | Design Document | Lead Designer | Technical Lead | Architects, Developers | Project Manager
Execution | Development Sprint | Development Team | Scrum Master | Product Owner | Stakeholders
Testing | Test Plan | QA Lead | Project Manager | Developers, Testers | Stakeholders
Testing | UAT Sign-off | Business Users | Product Owner | QA Team | Project Team
Deployment | Release Plan | Release Manager | Project Manager | Ops Team, Dev Team | All Stakeholders
Closure | Lessons Learned | Project Manager | Sponsor | All Team Members | Organization

## Instructions
RACI Matrix Template - Instructions
What is RACI?
RACI is a responsibility assignment matrix that clarifies roles and responsibilities:
• R - Responsible: The person(s) who does the work to complete the task
• A - Accountable: The person ultimately answerable for the correct completion (only ONE per task)
• C - Consulted: People who provide input and must be consulted before decisions are made
• I - Informed: People who need to be kept informed of progress or decisions
How to Use This Template:
1. List your project milestones in the 'Milestone' column
2. Break down each milestone into specific deliverables or tasks
3. Assign team members or roles to each RACI category
4. Ensure each deliverable has exactly ONE Accountable person
5. Multiple people can be Responsible, Consulted, or Informed (separate with commas)
Tips for Success:
• Keep deliverables specific and measurable
• Avoid having too many people in Consulted - it slows decisions
• The Accountable person has veto power and final say
• Use job titles or names consistently throughout
• Review and update the matrix as the project evolves
Using with M365 Copilot:
You can use Copilot to help populate this matrix. Try prompts like:
'Based on the project team list, fill in RACI assignments for these deliverables'
'Review this RACI matrix and identify any gaps or conflicts'
'Suggest additional deliverables for the Planning milestone'

## Activities
Milestone | Deliverable
Planning | Plan A
Planning | Plan B
Planning | Etc…
Planning
Planning

## Participants
Name | IsTeam | Description
DevOps | X | Reponsible for DevOps related activities
Bob Smith |  | Project manager. Responsible for signing-off on activities as they are planning and delivered